Thursday, March 14, 2019

Five milestones of CE-TOF mechanical design

James Xia

Today Paul, Houle, and I discussed on CE-TOF timeline and came up with five milestones:

- First milestone: completion of conceptual and preliminary design (4 weeks | by April 17th)
Embody parts: ion source, quadrupole ion transfer line, pusher, reflectron, MCP detector, reflectron, mounting and vacuum sealing of components.

- Second milestone: completion of 3D CAD model (5 weeks | by May 30th)
Detailed engineering design, solid modeling and specifications.

- Third milestone: completion of engineering drawings for machining (3 weeks | by June 20th)
Finalizing engineering drawings and identifying machine shops to make the parts.

- Fourth milestone: all parts in house (8 weeks | by August 20th) 
Vigorous inspection on all parts.

- Fifth milestone: start pumping (2 weeks | by September 5th)